## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
JULY 2020

## Slide 2: RECENT PROGRESS – NW Lot at 7th and Cherry
Restoration of NW lot began
  Concrete poured:
    Streets, curbs, sidewalks along
    Cherry Street, 7th Street, and HGI
    HGI Porte Cochere
    HGI Dumpster Pad

## Slide 3
RECENT PROGRESS – Finish Concrete Work around HGI and NW Lot
1
2
3
4

## Slide 4
RECENT PROGRESS – State Office Parking Lot
State Office Parking Lot at 8th and Cherry
  Closed Lot for tree demolition
  Began sewer tap and sewer pipe installation

## Slide 5
RECENT PROGRESS – State Office Parking Lot – Looking North
Before
After

## Slide 6
RECENT PROGRESS – 8th and Cherry Sewer Tap Installation
Before
After

## Slide 7
RECENT PROGRESS – 8th and Cherry Sewer Installation

## Slide 8
Continuation of utility installations to the east
Demo HGI NW lot, trees, shrubs, curbing, sidewalks, etc.
Install water meter pit at HGI East entrance week of July 20th
Installation of Storm Trap on HGI north lot – Scheduled to begin July 27th
Closing of 8th Street permanently – August 31, 2020
Restoration of HGI north lot complete by September 11, 2020
UPCOMING ACTIVITIES

## Slide 9
What is a PR? – Proposal Request
  Request for pricing that outlines additional work being considered by the owner
What is an ASI? – Architects Supplemental Instructions
  Formal notice issued from the architect to provide additional information
What is a CO? – Change Order
  Modification to the GMP that alters the scope of work, schedule, and/or pricing
What is an RFI? – Request For Information
  Formal process of questions and answers between designers and contractors
What is an Allowance?
  Amount specified in the contract for items not fully determined at time of contracting, then reconciled via change order once information is available
FAQ’s Regarding Construction Projects

## Slide 10
Distribution to all CIB members
Reports contain the following:
  Executive Summary
  Construction Budget Summary
  Updated Schedule
  Photos
MONTHLY CONSTRUCTION REPORTS

## Slide 11: QUESTIONS?