## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
March 2021

## Slide 2
CONSTRUCTION OVERVIEW
Budget:
  Current GMP amount is $26,325,510
Schedule:
  Project is on schedule. Substantial completion date is April 27, 2022
Recent progress:
  Parking Garage precast panel installation is 50% complete
  Convention Center exterior framing and sheathing is 50% complete
  Convention Center concrete slabs are complete
  Convention Center stairs have been installed

## Slide 3
CONSTRUCTION OVERVIEW
Upcoming activities:
  NE Garage
    Precast concrete installation continues
  Convention Center
    Roofing begins
    Interior framing begins
    Masonry – Interior CMU begins
    Above-ceiling MEP begins
    Exterior framing and sheathing continues
    Slab on Deck

## Slide 4: RECENT PROGRESS – Convention Center – February 2021

## Slide 5: RECENT PROGRESS – Convention Center – March 2021

## Slide 6: RECENT PROGRESS – Pre-function Area and Ballroom Preparation for concrete

## Slide 7: RECENT PROGRESS – Pre-function Area and Ballroom concrete complete

## Slide 8: RECENT PROGRESS – Parking Garage – February 2021

## Slide 9: RECENT PROGRESS – Parking Garage – March 2021

## Slide 10: QUESTIONS?