## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
April 2021

## Slide 2
CONSTRUCTION OVERVIEW
Recent progress:
  Parking Garage
    Precast panel installation is nearing completion
  Convention Center
    Exterior framing and sheathing is 75% complete (including air/moisture barrier)
    Stairs – concrete infill complete
    Interior masonry walls (back of house) - complete
    Exterior masonry veneer (west elevation) began
    MEP overhead installations are 50% complete
    Interior framing is 75% complete

## Slide 3
CONSTRUCTION OVERVIEW
Upcoming activities:
  NE Garage
    Concrete floor slabs
  Convention Center
    Roofing to be completed this week
    Interior framing continues
    Exterior framing and sheathing continues
    EIFS begins
    Masonry – Exterior masonry continues
    Limestone veneer on south elevation begins
    Above-ceiling MEP continues
    Skylight installation begins

## Slide 4: RECENT PROGRESS – Convention Center – April 2021

## Slide 5: RECENT PROGRESS – Exterior Framing and Sheathing

## Slide 6: RECENT PROGRESS – Air and Moisture Barrier Application

## Slide 7: RECENT PROGRESS – Interior Masonry (Back of House)

## Slide 8: RECENT PROGRESS – Exterior Masonry

## Slide 9: RECENT PROGRESS – Overhead MEP and restroom rough-in

## Slide 10: RECENT PROGRESS – Pre-function Area and Ballroom Interior Framing & Drywall

## Slide 11: RECENT PROGRESS – Ready for Skylight installation

## Slide 12: RECENT PROGRESS – Parking Garage – April 2021

## Slide 13
CONSTRUCTION OVERVIEW
Budget:
  Current GMP amount is $26,392,808
    Changes this period – Change Order No. 9: $67,298
      Kitchen and Door Revisions: $35,943
      HGI Connector Finish Revisions: ($33,232)
      Garage Elevator Wall Revision: $15,337
      Fabric Wrapped Panel Facing Material Revision: $12,135
      Miscellaneous Electrical Revisions: $4,650
      Water Service Tap Revision: $41,282
      Delete Unnecessary Roof Drains: ($2,861)
      Exterior Wall Insulation Revisions: ($5,956)
Schedule:
  Project is on schedule. Substantial completion date is April 27, 2022

## Slide 14: QUESTIONS?