## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
May 2021

## Slide 2
CONSTRUCTION OVERVIEW
Budget:
  Current GMP amount is $26,392,808
    No change orders this period
Schedule:
  Project is on schedule. Substantial completion date is April 27, 2022

## Slide 3
CONSTRUCTION OVERVIEW
Recent progress:
  Convention Center
    Exterior framing and sheathing is complete (including air/moisture barrier)
    Exterior masonry veneer complete on north, west, and east elevations
    Interior wall framing and in-wall blocking is complete
    Roof top air handling units are installed
    Skylight installation is complete
    Water main tap and piping is complete
    Electrical gear is installed
  Parking Garage
    Precast panel installation is complete

## Slide 4
CONSTRUCTION OVERVIEW
Upcoming activities:
  Convention Center
    EIFS continues
    Exterior masonry continues
    Limestone veneer continues
    MEP rough-in continues
    Install monumental stairs
    Elevator installation begins June 7th
    Storefront frame installation will begin June 1st
  Parking Garage
    Concrete floor slabs will begin May 24th
    Elevator installation begins June 23rd

## Slide 5: RECENT PROGRESS – Convention Center – May 2021

## Slide 6: RECENT PROGRESS – Skylight installed

## Slide 7: RECENT PROGRESS – Exterior Masonry Veneer – East Elevation

## Slide 8: RECENT PROGRESS – Exterior Insulation and Finish System (EIFS) – West Elevation

## Slide 9: RECENT PROGRESS – Overhead MEP

## Slide 10: RECENT PROGRESS – Interior Drywall installation

## Slide 11: RECENT PROGRESS – Interior Framing and In-wall Blocking

## Slide 12: RECENT PROGRESS – Interior Framing and In-wall Blocking

## Slide 13: RECENT PROGRESS – Parking Garage – May 2021

## Slide 14: RECENT PROGRESS – Parking Garage 3rd Floor and 5th Floor

## Slide 15: QUESTIONS?