## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
June 2021

## Slide 2
CONSTRUCTION OVERVIEW
Budget:
  Current GMP amount is $26,392,808. No change this period
    Change Order No. 10 is pending final approval: $142,301
      Includes the following: added PG storage room, office revisions, added traffic arm, added museum door, fire alarm revisions, DAS site survey, added sanitary wall cleanout, revised north canopy framing, elevator flooring revisions
Schedule:
  Project is on schedule. Substantial completion date is April 27, 2022

## Slide 3
CONSTRUCTION OVERVIEW
Recent progress:
  Convention Center
    Exterior masonry veneer complete on north, west, and east elevations
    EIFS on West Elevation completed
    Storefront framing began along Wabash Ave.
    Operable Panel Partitions track installed
    Monumental Stair installed
    Bulkhead framing and Drywall installation is progressing
    MEP Rough-in continues
  Parking Garage
    Concrete topping slabs have begun
    Backfill for slab on grade is underway
    Exterior and interior touch ups to pre-cast panels

## Slide 4
CONSTRUCTION OVERVIEW
Upcoming activities:
  Convention Center
    EIFS continues, work now taking place on south elevation
    Limestone veneer to be completed
    Elevator installation has begun
    Glass installation to begin along Wabash Ave.
    Window frame installation on east and north elevations
    Drywall hanging will progress as building becomes enclosed
    MEP rough-in continues
    Exterior hardscape and HGI connector
  Parking Garage
    Concrete topping slabs will continue
    Elevator installation begins

## Slide 5: RECENT PROGRESS – Convention Center – June 2021

## Slide 6: RECENT PROGRESS – East Elevation

## Slide 7: RECENT PROGRESS – Ballroom Ceiling Framing

## Slide 8: RECENT PROGRESS – Exterior Insulation and Finish System (EIFS) – West Elevation

## Slide 9: RECENT PROGRESS – South Elevation – Window Framing

## Slide 10: RECENT PROGRESS – Interior Drywall and Monumental Stair Installation

## Slide 11: RECENT PROGRESS – Parking Garage Level 4 Reinforcing Steel

## Slide 12: RECENT PROGRESS – Parking Garage Rooftop Concrete Slab

## Slide 13: QUESTIONS?