## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
December 2021

## Slide 2
CONSTRUCTION OVERVIEW
Budget:
  Current GMP amount is $27,108,324 (as of December 14th, 2021)
  Changes from previous GMP: CO NO. 14; $33,290 (Graffiti sealer, added door, decorative panel at N entrance)
Schedule:
  Project is on schedule. Original substantial completion date is April 27, 2022
  Anticipated new substantial completion date is March 3, 2022.
Design:
  Museum underslab electrical design received 12/14. Pricing is being developed.

## Slide 3
CONSTRUCTION OVERVIEW
Recent progress:
  Convention Center
    Ceiling tile installation
    Wood/fabric paneling substantially complete
    Terrazzo flooring complete
    Light fixture installation complete
    Interior storefront and glazing complete
    Sitework 95% complete
    Asphalt paving complete
    Irrigation and planting 95% complete, sod installation
    HGI Connector dried-in and drywall hung
    Decorative railing installation
  Parking Garage
    Parking Garage Elevators nearing completion
    Parking Garage stairwell painting complete
    Parking striping complete

## Slide 4
CONSTRUCTION OVERVIEW
Upcoming activities:
  Convention Center
    Finish coat paint
    Complete ceiling tile installation
    Install restroom vanities
    Install carpet
    Install kitchen equipment
    Install decorative panels
    Begin door/hardware install
    Mechanical equipment startup
    Irrigation/planting complete
    Connector substantially complete
    Elevator inspection and final permit
  Parking Garage
    Elevator inspection and final permit
    Parking garage completion

## Slide 5: RECENT PROGRESS – Convention Center – November 2021

## Slide 6: RECENT PROGRESS – Main entrance

## Slide 7: RECENT PROGRESS – South Elevation

## Slide 8: RECENT PROGRESS – East Elevation

## Slide 9: RECENT PROGRESS – Ballroom

## Slide 10: RECENT PROGRESS – Pre-function Area

## Slide 11
RECENT PROGRESS – Lobby

## Slide 12
RECENT PROGRESS – Monumental Stair & Decorative Railing

## Slide 13
RECENT PROGRESS – Kitchen Equipment Installation

## Slide 14
RECENT PROGRESS – Lobby Decorative Panels

## Slide 15
RECENT PROGRESS – Terrazzo Flooring

## Slide 16
RECENT PROGRESS – Meeting Room Mullions

## Slide 17
RECENT PROGRESS – Limestone Sign

## Slide 18
RECENT PROGRESS – East Elevation

## Slide 19
RECENT PROGRESS – Convention Center North Parking

## Slide 20
RECENT PROGRESS – Parking Garage West Elevation

## Slide 21
RECENT PROGRESS – Parking Garage North Elevation

## Slide 22
RECENT PROGRESS – Parking Garage East Elevation

## Slide 23
RECENT PROGRESS – Parking Garage South Elevation

## Slide 24
RECENT PROGRESS – Parking Garage South Entrance Canopy Column Covers

## Slide 25
RECENT PROGRESS – Parking Garage 5th Floor

## Slide 26: RECENT PROGRESS – HGI Connector

## Slide 27
RECENT PROGRESS – HGI Connector Interior

## Slide 28: QUESTIONS?