## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
February 2021

## Slide 2
CONSTRUCTION OVERVIEW
Budget:
  Current GMP amount is $26,325,510
Schedule:
  Project is on schedule. Substantial completion date is April 27, 2022
Recent progress:
  NE Garage precast panel installation has begun (25 of 370 pieces erected)
  Structural Steel work is complete at Convention Center with detailing and decking ongoing
  Convention Center exterior framing and sheathing has begun
  Convention Center Slab on Grade and underslab MEP work continues
  Mock-up has undergone architectural review

## Slide 3
CONSTRUCTION OVERVIEW
Upcoming activities:
  NE Garage
    Precast concrete installation
  Convention Center
    Completion of under slab plumbing
    Concrete slab on grade
    Steel stair installation
    Exterior framing and sheathing

## Slide 4: RECENT PROGRESS – Convention Center Structural Steel nearing completion

## Slide 5: RECENT PROGRESS – Convention Center Framing & Sheathing And Radiant Heat Flooring in Pre-function Area

## Slide 6: RECENT PROGRESS – NE Garage Pre-cast panel erection has begun

## Slide 7: RECENT PROGRESS – Mock-up for architectural review

## Slide 8: QUESTIONS?