## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
October 2020

## Slide 2
CONSTRUCTION OVERVIEW
Project remains on schedule and within budget
Recent progress:
  Convention Center site demolition (East lot of HGI to Copper Bar) complete
  Electrical switchover is complete (old underground network de-energized 10/12/2020)
  Auger cast piles: Mobilization and test piles have begun
  NE Garage site demo and prep for Storm Trap is complete
Upcoming activities:
  Install NE Garage Storm Trap
  Begin Convention Center and NE Garage production auger cast piles

## Slide 3: RECENT PROGRESS – Site Demolition – 9/15/2020

## Slide 4: RECENT PROGRESS – Site Demolition – 9/27/2020

## Slide 5: RECENT PROGRESS – NE Garage StormTrap prep

## Slide 6: RECENT PROGRESS – Auger Cast Test Piles

## Slide 7: RECENT PROGRESS – Auger Cast Piles – Testing

## Slide 8
Auger Cast Pile Installation begins October 20, 2020
StormTrap Delivery: October 20, 2020
Concrete Foundations begin October 26, 2020
Structural Steel Delivery: November 13, 2020
PROJECT MILESTONES

## Slide 9: QUESTIONS?