## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
November 2020

## Slide 2
CONSTRUCTION OVERVIEW
Project remains on schedule and within budget
Recent progress:
  Convention Center auger cast pile installation is complete - 177
  NE Garage auger cast pile installation will be complete 11/18/2020 - 247
  Foundation work has begun
Upcoming activities:
  Convention Center foundation and grade beams continue
  Structural Steel, Joists, and Decking installation begins

## Slide 3: Auger Cast Pile - Convention Center (177 total)

## Slide 4: Auger Cast Pile – NE Garage (247 total)

## Slide 5: RECENT PROGRESS – Auger Cast Pile

## Slide 6: RECENT PROGRESS – Foundations Begin

## Slide 7: RECENT PROGRESS – Grade Beams

## Slide 8
Auger Cast Pile Installation Complete: November 18, 2020
Convention Center Foundation work Complete: December 4, 2020
Structural Steel Delivery: December 7, 2020
NE Garage Foundation Work to begin: December 7, 2020
NE Garage Foundation Work Complete: January 30, 2020
PROJECT MILESTONES

## Slide 9: QUESTIONS?