## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
December 2020

## Slide 2
CONSTRUCTION OVERVIEW
Project remains on schedule and within budget
Recent progress:
  Convention Center foundations, damp-proofing and backfill is complete
  NE Garage foundation work has begun
  Structural Steel erection began this week
Upcoming activities:
  NE Garage foundations continue
  Structural Steel, Joists, and Decking continues

## Slide 3: RECENT PROGRESS – Foundation work in progress (Convention Center)

## Slide 4: RECENT PROGRESS – Foundation work Complete (Convention Center)

## Slide 5: RECENT PROGRESS – Crane Mobilization and Structural Steel Erection – Day 1

## Slide 6
Convention Center Foundation Work Completed: December 11, 2020
Structural Steel Erection Started: December 14, 2020
NE Garage Foundation Work Began: December 14, 2020
NE Garage Foundation Work Complete: January 30, 2021
NE Garage Precast Delivery: February 1, 2021
Structural Steel – Convention Center Completion: February 9, 2021
PROJECT MILESTONES

## Slide 7: QUESTIONS?