## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
January 2021

## Slide 2
CONSTRUCTION OVERVIEW
Budget:
  Current GMP amount is $26,325,510
Schedule:
  Project is on schedule. Substantial completion date is April 27, 2022
Recent progress:
  NE Garage foundation work is 95% complete
  Structural Steel work continues
  Underslab MEP work has begun
  Mock-up is nearing completion for architectural review

## Slide 3
CONSTRUCTION OVERVIEW
Upcoming activities:
  Delivery and installation of garage pre-cast concrete
  Completion of structural steel framing, joists and decking
  Continuation of underslab plumbing
  Concrete slab installation
  Steel stair installation
  Exterior framing and sheathing

## Slide 4: RECENT PROGRESS – Convention Center

## Slide 5: RECENT PROGRESS – NE Garage

## Slide 6: QUESTIONS?

## Slide 7
TERRE HAUTE CONVENTION CENTER
PROJECT OVERVIEW
January 2021

## Slide 8
Project Facts
Who is the Owner?
CIB – Capital Improvement Board
Who are the Architects?
CSO Architects – Indianapolis
Who is the Owners Representative?
Nations Group
Who represents the Garmong Team?
Brian Kooistra, COO
Lance Gassert, VP
Mark Merrill, Project Manager
Steve Elkins, Superintendent
Marla Flowers, Project Engineer

## Slide 9
FAQ
Who are our major local subcontractors?
Ace Blind & Drapery
B & S Plumbing
Dennis Trucking
Central Indiana Ready-Mix
Crossroads Door & Hardware
Lee Company
Overhead Door Company of Terre Haute
SDR Coatings
SMC
Strode Construction
Sycamore Engineering

## Slide 10
Site Plan

## Slide 11
Convention Center – East View

## Slide 12
Convention Center – West View

## Slide 13
Convention Center - Spine

## Slide 14
Convention Center – Pre-Function

## Slide 15
Convention Center - Ballroom

## Slide 16
Convention Center – Larry Bird Museum

## Slide 17
Convention Center – South Courtyard

## Slide 18
Convention Center – North Courtyard

## Slide 19
Northeast Garage

## Slide 20
First Floor Plan

## Slide 21
Second Floor Plan

## Slide 22
Banquet Layout Options

## Slide 23
Theatre Layout Options

## Slide 24
Classroom Layouts

## Slide 25
Breakout Layouts

## Slide 26
Tradeshow Layout Option

## Slide 27
Fun Facts
Fun Facts:
How many square feet is the Convention Center?
41,000 sf
How many square feet is the Ballroom?
12,550 sf
How many seats can the Ballroom accommodate?
900
How many parking spaces in the Parking Garage?
460

## Slide 28: QUESTIONS?