## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
August 2021

## Slide 2
CONSTRUCTION OVERVIEW
Budget:
  Current GMP amount is $26,958,850 (as of August 16, 2021)
  Changes from previous GMP: CO NO. 11; $423,741
Schedule:
  Project is on schedule. Original substantial completion date is April 27, 2022
  Anticipated new substantial completion date is March 1, 2022.

## Slide 3
CONSTRUCTION OVERVIEW
Recent progress:
  Convention Center
    Drywall finishing taking place in pre-function and ballroom areas
    EIFS on North elevation is complete
    Glass installation is substantially complete
    Gutters and downspouts have started
    Remaining site utilities are being completed
    Connector foundations are installed
  Parking Garage
    Electrical installations are taking place
    SOG ready to pour

## Slide 4
CONSTRUCTION OVERVIEW
Upcoming activities:
  Convention Center
    Complete EIFS
    Painting will begin
    Installation of front and rear entrances
    Exterior hardscape begins (between Copper Bar and along Wabash Ave.)
    HGI connector steel
  Parking Garage
    First floor concrete slab
    Roof installation over stairs and elevator shafts
    Elevator installation begins

## Slide 5: RECENT PROGRESS – Convention Center – August 2021

## Slide 6: RECENT PROGRESS – South Elevation

## Slide 7: RECENT PROGRESS – Larry Bird Museum

## Slide 8: RECENT PROGRESS – East Elevation

## Slide 9: RECENT PROGRESS – North Elevation

## Slide 10: RECENT PROGRESS – Second Floor Northeast View

## Slide 11: RECENT PROGRESS – Ballroom

## Slide 12: RECENT PROGRESS – Pre-function Area

## Slide 13
RECENT PROGRESS – Kitchen Fume Hood

## Slide 14
RECENT PROGRESS – Elevator

## Slide 15: RECENT PROGRESS – HGI Connector Location

## Slide 16
RECENT PROGRESS – Convention Center South Entrance

## Slide 17
RECENT PROGRESS – Convention Center Sign Wall

## Slide 18
RECENT PROGRESS – Convention Center North Entrance

## Slide 19: QUESTIONS?