## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
October 2021

## Slide 2
CONSTRUCTION OVERVIEW
Budget:
  Current GMP amount is $27,075,034 (as of October 19, 2021)
  Changes from previous GMP: CO NO. 13; $78,175
Schedule:
  Project is on schedule. Original substantial completion date is April 27, 2022
  Anticipated new substantial completion date is March 1, 2022

## Slide 3
CONSTRUCTION OVERVIEW
Recent progress:
  Convention Center
    Drywall finishing ongoing 2nd Floor
    Painting complete in Ballroom, started on east
    Restroom ceramic wall and floor tile complete on 1st floor, started on 2nd
    Walk in cooler/freezer installation is complete
    Ceiling grid installation is 50% complete
    Roof coping is nearing completion
    Metal panel installation is nearing completion
    Wood paneling 50% complete
    FRP in kitchen has begun
    Site hardscape is well underway
  Parking Garage
    Light fixture installation is 75% complete
    Elevator installation is 70% complete
    Southwest curtainwall is complete

## Slide 4
CONSTRUCTION OVERVIEW
Upcoming activities:
  Convention Center
    Complete painting and ceiling grid
    Install light fixtures
    Ceramic tile on 2nd floor
    Complete wood paneling
    Install plumbing fixtures
    HVAC fully functional
    Terrazzo flooring in corridor
    Epoxy flooring in kitchen
    Interior glass and glazing
    Exterior glass canopy
    Substantially complete site work
    Connector weather tight
  Parking Garage
    Nearing substantial completion of garage

## Slide 5: RECENT PROGRESS – Convention Center – September 2021

## Slide 6: RECENT PROGRESS – South Elevation

## Slide 7: RECENT PROGRESS – Larry Bird Museum

## Slide 8: RECENT PROGRESS – East Elevation

## Slide 9: RECENT PROGRESS – North Elevation

## Slide 10: RECENT PROGRESS – Ballroom

## Slide 11: RECENT PROGRESS – Pre-Function Area

## Slide 12
RECENT PROGRESS – Lobby

## Slide 13
RECENT PROGRESS –Kitchen Walk-In Freezer

## Slide 14
RECENT PROGRESS – Kitchen FRP Installation

## Slide 15
RECENT PROGRESS – Main Entry Storefront

## Slide 16: RECENT PROGRESS – HGI Connector Location

## Slide 17
RECENT PROGRESS – Restroom Tile

## Slide 18
RECENT PROGRESS – Convention Center Decorative Paving

## Slide 19
RECENT PROGRESS – Parking Garage South Elevation Curtainwall

## Slide 20
RECENT PROGRESS – Parking Garage Elevators

## Slide 21
RECENT PROGRESS – Parking Garage West Elevation Limestone Planters/ Benches

## Slide 22
RECENT PROGRESS – Parking Garage South Elevation

## Slide 23: QUESTIONS?