## Slide 1
TERRE HAUTE CONVENTION CENTER
CONSTRUCTION UPDATE
November 2021

## Slide 2
CONSTRUCTION OVERVIEW
Budget:
  Current GMP amount is $27,075,034 (as of November 17, 2021)
  Changes from previous GMP: CO NO. 13; $78,175
Schedule:
  Project is on schedule. Original substantial completion date is April 27, 2022
  Anticipated new substantial completion date is March 1, 2022.
Design:
  No plans received to date on museum

## Slide 3
CONSTRUCTION OVERVIEW
Recent progress:
  Convention Center
    Restroom ceramic tile and floor tile complete
    Kitchen flooring
    Ceiling grid
    Wood paneling
    Fabric panels
    Terrazzo flooring
    Toilet partitions
    Plumbing fixtures
    Lighting fixtures
    Sliding entrance doors
    Glass canopy
  Parking Garage
    Light fixture installation
    Traffic coating
    Painting
    Elevator installation nearing completion

## Slide 4
CONSTRUCTION OVERVIEW
Upcoming activities:
  Convention Center
    Operable partitions
    Interior glass and glazing
    Complete terrazzo flooring
    Decorative handrail
    Carpet
    Complete wood paneling
    Countertops and vanities
    Parking lot asphalt
    Kitchen equipment installation
    Toilet accessories
    Limestone for signs
    Connector weather tight
  Parking Garage
    Substantial completion of garage

## Slide 5: RECENT PROGRESS – Convention Center – November 2021

## Slide 6: RECENT PROGRESS – South Elevation

## Slide 7: RECENT PROGRESS – Main entrance

## Slide 8: RECENT PROGRESS – East Elevation

## Slide 9: RECENT PROGRESS – Ballroom

## Slide 10: RECENT PROGRESS – Pre-function Area

## Slide 11
RECENT PROGRESS – Lobby

## Slide 12
RECENT PROGRESS –Kitchen

## Slide 13
RECENT PROGRESS – Restrooms

## Slide 14
RECENT PROGRESS – Terrazzo Flooring Installation

## Slide 15
RECENT PROGRESS – Main Entry Sliding Doors

## Slide 16
RECENT PROGRESS – Glass Canopy at South Entrance

## Slide 17
RECENT PROGRESS – Landscaping

## Slide 18
RECENT PROGRESS – Parking Garage West Elevation

## Slide 19
RECENT PROGRESS – Parking Garage South Entrance Sidewalk and Paver Location

## Slide 20
RECENT PROGRESS – Parking Garage 5th Floor Traffic Coating

## Slide 21: RECENT PROGRESS – HGI Connector EIFS Installation

## Slide 22: QUESTIONS?